## CI-CD
CI-CD Pipeline Creation
Jenkins Installion
Version Control System | GitLab
Artifact Management
Set up the artifact repository (Nexus) | Nexus
creating proxy repo for Maven and NodeJS build dependencies
Define CI-CD Jobs for build,test and Deployment stages | Jenkins
Pipeline Scripting | Groovy (Jenkinsfile) shared libraries
Integration with VCS
Required dependencies and plugins for build creation and Integration with multiple tools
Creating build script as three parameter DEV, UAT, PROD
Creating build script (Maven, npm)
Integration with Nexus
Integration with SonarQube
Containerization
Creating Dockerfiles for application components
Setting up Container registry
Deployment Scripts
Writing Deployment scripts for different environments kubernetes manifest
FOR BACKEND SERVICES CI-CD Process in Gitlab | FOR UI CI-CD Process in Gitlab
Common Jenkinsfile for all below services
AdministrationService
AuthenticationService
EmigrantService
ForeignRecruiterService
GatewayService
GrievanceService
InsuranceService
IntegrationService
NotificationService
PaymentService
RecruitingAgentService
ReportService
SecurityService
WorkflowService
CI Steps
tools
Stage -1
1) Checkout SCM
Integration with Gitlab
Required dependencies and plugins to be install
Stage-2
2) Declarative: Tool Install
Required dependencies and plugins to be install
Stage-3
3) Maven build
Intgerate with Nexus to download required dependencies using settings.xml
Stage-4
4)Static Code Analysis
Integration with SonarQube
Intgerate with Nexus to download required dependencies using settings.xml
Stage-6
7) Build and Push Docker Image to Nexus
Docker Installation and establishing connection between nexus and docker
Integration with Nexus
Required dependencies and plugins to be install
CD Steps
Stage-7
8) Deployment to K8S
Creating Dockerfile and K8S Manifest
Required plugins to be installed to intract with K8S cluster
Deploying the images to specific namespace
Stage-8
8) Monitoring Deployment
Monitoring deployed pod status and failure on the basis of pod status
https://medium.com/edureka/jenkins-x-d87c0271af57

## K8S-Setup_plan
| Task | Effort in PD | NoOfDays | Start Date | End Date | Team | Team members | Remarks
Infra Provisoning - VM | Build Server - Ansible / Python 3 ( Install , 16G RAM , 8 Cores, 250 GB storage, Red Hat >= 9.3(Production) |  |  |  |  | IT Team
| 3 K8 Master Nodes (8GB RAM, 4 cores, 50 GB storage, Redhat 9.3) |  |  |  |  | IT Team
| 2 VMs for LB ( 2core, 4GB RAM, 20GB storage) with virtual IP |  |  |  |  | IT Team
| 5 K8 Worker Nodes (16GB RAM, 8 cores, 50 GB storage, Redhat 9.3) + 200GB block storage |  |  |  |  | IT Team
| Devops - Nexus ( 16GB RAM, 8 core, 50GB storage, 2x250GB NFS mount, RHEL 9.3 ) |  |  |  |  | IT Team
| CICD - 1 Master , 2 Slave ( Jenkins Server) - 8 cores, 16GB RAM, 50GB storage(Slave), 4 cores, 8G, 20GB storage(Master) |  |  |  |  | IT Team
| Sudo access on all the servers |  |  |  |  | IT Team
| Another HAProxy LB with virtual IP for DR reverse proxy |  |  |  |  | IT Team
| Valid RedHat subscription needed - credentials required |  |  |  |  | IT Team
K8 Cluster setup | Airgap installation( making a copy of all the images in local machine),K8 Cluster setup - through Ansible scripts | 15 | 15 | 2024-05-24 | 2024-06-14 | Arch Team | Amit & Suresh
Transitive dependencies for artifacts in Nexus
| Settting up BLOCK storage using longhorn | 2 | 2 | 2024-06-17 | 2024-06-19 | Arch Team | Amit & Suresh
| Nginx Ingress Controller setup | 5 | 3 | 2024-06-17 | 2024-06-20 | Arch Team | Siddharth, Chiransh & Suresh
| Service Mesh setup - (Istio) | 15 | 5 | 2024-06-21 | 2024-06-28 | Arch Team | Siddharth, Chiransh & Suresh
| Create docker file and K8 manifest files | 8 | 4 | 2024-05-24 | 2024-05-30 | Arch Team | Anil & Suresh
| Creating a sample CICD pipeline(DEV, UAT, PROD) | 10 | 4 | 2024-05-24 | 2024-05-30 | Arch Team | Siddharth, Chiransh, Amit & Suresh
| Deploying a sample existing emigrate Service in K8 cluster & sanity testing | 8 | 2 | 2024-05-31 | 2024-06-04 | Arch Team | Siddharth, Chiransh, Anil & Suresh
| Build Promotion Strategy for Release management(DEV, UAT, PROD) | 4 | 4 | 2024-05-31 | 2024-06-06 | Arch Team | Amit, Anil & Suresh | We can use namespace strategy
| Build Promotion Implementation for Release management(DEV, UAT, PROD), namespace creation for different env | 15 | 10 | 2024-06-05 | 2024-06-19 | Arch Team | Siddharth, Chiransh & Suresh
| Upgradation procedure, Cerificate Rotation for K8 Master and Worker nodes | 6 | 3 | 2024-06-20 | 2024-06-25 | Arch Team | Amit & Suresh
Monitoring | Prometheus and Grafana , alert manager | 12 | 4 | 2024-06-26 | 2024-07-02 | Arch Team | Amit, Anil & Suresh | Some code changes may required.
| Integration of vunet with K8 cluster and support required from External/Vunet needed | 2 | 1 | 2024-06-05 | 2024-06-06 | Arch Team/ IT Team | Kiran ,Anil & Suresh | Setup a meeting in last week of May to understand the capabilities of vunet tool for monitoring the K8S cluster. Based on the outcome of this meeting, the need for prometheus & grafana will be decided
1 day to provide required input from application side to IT team . Implementation time we need to get from IT-team/Third-party team
Auto Scale | Auto Scaling / KEDA for autoScaling / Custom metrics/ HPA | 21 | 7 | 2024-07-03 | 2024-07-12 | Arch Team | Amit, Anil & Suresh
Testing | Load test script preparation and validation | 15 | 15 | 2024-05-29 | 2024-06-19 | Arch Team | Veera & Suresh
| Execution of load test scripts & performance tuning | 20 | 10 | 2024-07-15 | 2024-07-29 | Arch Team | Amit, Anil & Suresh
| Functional testing | 20 | 5 | 2024-06-20 | 2024-06-27 | QA Team | QA
Documentation | Objectives of POC , with a document indicating ( what is required, have we achieved and how to integrate with current prod | 1 |  | 2024-05-24 | 2024-07-19 | Arch Team | Anil, Amil & Suresh
| Installation , initial setup procedures, SOP procedures ( rotaiton of certifiates, upgradation....) | 4 |  | 2024-05-24 | 2024-07-19 | Arch Team | Anil, Amil & Suresh

## K8S-POC-setup
Requirements:
Build Server
Ansible v2.14+, Jinja 2.11+ and python-netaddr is installed on the machine that will run Ansible commands
Python3 version 3.11.2 is required
Ansible Core Version 2.14.3 is required
Jinja Version 3.1.2 is required
Git
The firewalls are not managed. We will implement our own rules and during script invocation firewall will be disabled
Non root account with full sudo privileges will be required.
Temporary internet access for downloading the above packages
A valid Redhat Subscription manager will be required to be attached to this machine.
Download Server
Download Server with full internet access will be required
Unmanaged firewall. We will manage the firewall on this machine
Non root user with sudo priveleges
Code Repository hosted for this Setup:
https://github.com/amitbansal26/kubernetes-setup
S.No | Ansible Role | Servers to be run on | Purpose
1 | pkg-download | Download Server | 1. Install yum utils
2. Add kubernetes Repository
3. Add Docker Repository
4. Download only Kubernetes packages
5. Download haproxy packages
6. Download keepalived process
7. Download all the required docker images for cluster bootstrap
8. Create Tar Zip of RPM packages
9. Create Tar Zip of saved images
2 | pkg-xfer-remote | k8s-master | 1. Transfer all image tarball to remote servers
|  | k8s-worker | 2. Transfer kubernetes package tarball to remote server
3 | lb-xfer-remote | K8s-worker, k8s-master, | 1. Transfer haproxy packages to remote server
2. Transfer keepalived process to remote server
4. | unzip-artifacts |  | 1. Unzips all the tarballs into respective servers
5. | config-iptables | K8s-worker, haproxy, master | 1. Configure iptables for Bridged traffic
6 | Disable-firewall | K8s-worker, k8s-master, k8s-haproxy | 1. Disable firewall
7. |  |  | 2.